## PDE (hidden)
Well Name:
API | Surface Legal Location | Field Name | Permit Number | State/Province | Well Configuration Type
Ground Elevation (ft) | Casing Flange Elevation (ft) | KB - Ground Distance (ft) | KB - Casing Flange Distance (ft) | Spud Date | Rig Release Date
Jobs
Job Category | Primary Job Type | Secondary Job Type | Start Date | End Date
Target Depth (ft-KB) |  |  | Target Formation
Objective
AFE
AFE Number | AFE Date | AFE Type | Supplemental AFE Number
Total AFE + Supplement Amount (Cost) | Total AFE Amount (Cost) |  | Total AFE Supplement Amount (Cost) |  | AFE Status
AFE Cost Breakdown
| Major Category Code | Minor Category Code | AFE Amount (Cost) | Supplement Date | Supplement Amount (Cost)

## Summary
Water Oak Renewables, LLC
Operator: |  | Project Name
Criterion Operating, LLC |  | Water Oak Z031D Drill, Complete & Equip
Well Name |  | Field Name |  | County | State/Province | API
Water Oak Z031D |  | Pleasant Bayou (Frio Geothermal) |  | Brazoria | Texas
Job Category |  | Primary Job Description |  | Formation | Total Depth, ft MD | Well Type
Development Drilling |  | Drill, complete & equip vertical geothermal SWD |  |  | 7700 | GT SWD
AFE Number |  | AFE Date | AFE Type | Total AFE, USD
|  | 2023-01-27 |  | 4553764
Supplemental AFE Number |  | Supplement AFE Date | Supplement AFE Total, USD | Total AFE + Supplement AFE, USD
|  |  | 0 | 4553764
AFE SUMMARY
Major | Operations Category | AFE Amount, USD | Supplement AFE, USD | Total DCE AFE + Supplement AFE, USD
2 | Drilling | 2285230 | 0 | 2285230
3 | Completion | 2095534 | 0 | 2095534
5 | Equip | 173000 | 0 | 173000
AUTHORIZATION FOR EXPENDITURES
Danny Rehg, co-founder & CEO |  | Sean Marshall, co-founder & CFO |  | Partner Approval
Jeff Toedter, VP of Engineering |  | Denise Knight, VP of Geology & Geophysics |  | Partner Approval

## Drilling
Water Oak Renewables, LLC
Operator: |  |  | Project Name
Criterion Operating, LLC |  |  | Water Oak Z031D Drill, Complete & Equip
Well Name |  |  | Field Name |  |  |  | County | State/Province | API
Water Oak Z031D |  |  | Pleasant Bayou (Frio Geothermal) |  |  |  | Brazoria | Texas
Job Category |  |  | Primary Job Description |  |  |  | Formation | Total Depth, ft MD | Well Type
Development Drilling |  |  | Drill vertical geothermal SWD |  |  |  |  | 7700 | GT SWD
AFE Number |  |  | AFE Date |  | AFE Type |  | Total DRL AFE, USD
|  |  | 2023-01-27 |  |  |  | 2285230
Supplemental AFE Number |  |  | Supplement AFE Date |  | Supplement DRL AFE, USD |  | Total DRL AFE + Supplement DRL AFE, USD
[5 empty] | 0 |  | 2285230
CAPITALIZED INTANGIBLE COSTS
Major | Minor | Definition | Type | Units | Unit Cost | Qty | Total Cost | Supplement Date | Supplement Cost | Comments
2 | 10 | Location Preparation |  |  |  |  | 420000 |  | 0
2 | 11 | Legal, Land, Damages & Title |  |  | 80000 |  | 80000
2 | 12 | Permitting, Regulatory |  |  | 10000 |  | 10000
2 | 14 | Road, Locations, Pits |  |  | 300000 |  | 300000
2 | 15 | Mouse/Rathole/Conductor |  |  | 30000 |  | 30000
2 | 16 | Cleanup
2 | 17 | Water Well Drill & Plug
2 | 20 | Drilling Operations |  |  |  |  | 596000 |  | 0
2 | 21 | Mob/Demob |  |  | 200000 |  | 200000
2 | 22 | Rig Contract | Daywork | $/day | 33000 | 12 | 396000 |  |  | - 4 days coring; 2 days logging
2 | 30 | Drilling Fluids |  |  |  |  | 227500 |  | 0
2 | 31 | Fuel, Lube |  |  | 35000 |  | 35000
2 | 32 | Mud, Chemicals & Fluids |  |  | 105000 |  | 105000
2 | 33 | Water & Trucking Costs |  |  | 70000 |  | 70000
2 | 34 | Fluid Disposal |  |  | 17500 |  | 17500
2 | 40 | Rental Equipment |  |  |  |  | 175500 |  | 0
2 | 41 | Rentals - Surface |  |  | 95500 |  | 95500
2 | 42 | BOP Stack & Pressure Control |  |  | 50000 |  | 50000
2 | 43 | Rotary Tools & Acc (TD, PS, RH)
2 | 44 | Mud Related Equipment |  |  | 15000 |  | 15000
2 | 45 | Rentals - Subsurface (pipe, BHA) |  |  | 15000 |  | 15000
2 | 50 | Cementing Services |  |  |  |  | 150000 |  | 0
2 | 51 | OCTG |  |  | 150000 |  | 150000
2 | 52 | Squeeze
2 | 53 | Plugs
2 | 60 | Wireline, Logging and Testing |  |  |  |  | 97378 |  | 0
2 | 61 | Mud Logging |  |  | 15000 |  | 15000
2 | 62 | MWD / LWD
2 | 63 | Open Hole Logging |  |  | 62378 |  | 62378
2 | 64 | Drill Stem Testing
2 | 65 | Coring - operational services
2 | 66 | Coring - SCAL, analysis
2 | 67 | Wireline - Other |  |  | 20000 |  | 20000
2 | 70 | Specialized Services |  |  |  |  | 101000 |  | 0
2 | 71 | HSE Equipment & Services
2 | 72 | Welding & Fabrication |  |  | 8000 |  | 8000
2 | 73 | Torque & Test
2 | 74 | Directional Drilling, DH Surveys |  |  | 25000 |  | 25000
2 | 75 | Casing Running Services |  |  | 28000 |  | 28000
2 | 76 | Tubular Inspection
2 | 77 | Fishing & Pipe Recovery
2 | 78 | Miscellaneous Services |  |  | 40000 |  | 40000
2 | 80 | Transportation |  |  |  |  | 70000 |  | 0
2 | 81 | Trucking |  |  | 70000 |  | 70000
2 | 82 | Hot Shot
2 | 83 | Air
2 | 84 | Marine
2 | 110 | Admin, Insurance & Labor |  |  |  |  | 71000 |  | 0
2 | 111 | Contract Supervision, Onsite & Office |  |  | 39000 |  | 39000
2 | 112 | Contract Labor - roustabout, etc |  |  | 7500 |  | 7500
2 | 114 | G&A Overhead |  |  | 9500 |  | 9500
2 | 115 | Payroll Labor
2 | 116 | Well Control Insurance & Services |  |  | 10000 |  | 10000
2 | 117 | Insurance - GenLiab & Umbrella |  |  | 5000 |  | 5000
2 | 118 | LIH Fees
2 | 500 | Miscellaneous Costs - Intangible |  |  |  |  | 0 |  | 0
2 | 510 | Contingencies
2 | 520 | Accrual
CAPITALIZED TANGIBLE COSTS
Major | Minor | Definition | Description |  | Unit Cost | Qty | Total Cost | Supplement Date | Supplement Cost
2 | 1000 | Tangible Equipment |  |  |  |  | 376852 |  | 0
2 | 1005 | Consumables - Bits, Mills, FE, etc | bits 40k, gen 20, FE 100k |  | 160000 |  | 160000
2 | 1010 | Drive Pipe
2 | 1015 | Conductor Pipe | 18-5/8" 85.2# X-56 |  | 120 | 100 | 12000
2 | 1020 | Surface Casing | 13-3/8" 54.5# J-55 STC |  | 72.66 | 2200 | 159852
2 | 1025 | Intermediate Casing
2 | 1030 | Drilling Liner
2 | 1035 | Contingency Liner
2 | 1040 | Contingency Tie-Back
2 | 1060 | Wellhead & Fittings | SLB A-Section $40k, 5ksi 13-3/8" |  | 45000 | 1 | 45000
2 | 1070 | Subsurface Equipment
2 | 1070 | Hanger Systems
2 | 1095 | Lost in Hole
2 | 1500 | Miscellaneous Costs - Tangible |  |  |  |  | 0 |  | 0
2 | 1510 | Contingencies
2 | 1520 | Accrual

## Completion
Water Oak Renewables, LLC
Operator: |  |  | Project Name
Criterion Operating, LLC |  |  | Water Oak Z031D Drill, Complete & Equip
Well Name |  |  | Field Name |  |  |  | County | State/Province | API
Water Oak Z031D |  |  | Pleasant Bayou (Frio Geothermal) |  |  |  | Brazoria | Texas
Job Category |  |  | Primary Job Description |  |  |  | Formation | Total Depth, ft MD | Well Type
Development Drilling |  |  | Complete vertical geothermal SWD |  |  |  |  | 7700 | GT SWD
AFE Number |  |  | AFE Date |  | AFE Type |  | Total CMP AFE, USD
|  |  | 2023-01-27 |  |  |  | 2095534
Supplemental AFE Number |  |  | Supplement AFE Date |  | Supplement CMP AFE, USD |  | Total CMP AFE + Supplement CMP AFE, USD
[5 empty] | 0 |  | 2095534
CAPITALIZED INTANGIBLE COSTS
Major | Minor | Definition | Type | Units | Unit Cost | Qty | Total Cost | Supplement Date | Supplement Cost | Comments
3 | 10 | Location Preparation |  |  |  |  | 13500 |  | 0
3 | 12 | Permitting, Regulatory |  |  | 1000 |  | 1000
3 | 14 | Road, Location |  |  | 12500 |  | 12500
3 | 16 | Cleanup
3 | 18 | Frac Pond, Impoundment
3 | 20 | Completion Unit |  |  |  |  | 0 |  | 0
3 | 21 | Mob/Demob
3 | 22 | Completion Rig Contract | Daywork | $/day | [5 empty] | - 4 days coring; 2 days logging
3 | 25 | Coiled Tubing Unit & Support Eqpmt | Daywork | $/day | [5 empty] | - 4 days coring; 2 days logging
3 | 27 | Snubbing Unit & Support Eqpmt | Daywork | $/day | [5 empty] | - 4 days coring; 2 days logging
3 | 30 | Completion Fluids |  |  |  |  | 35000 |  | 0
3 | 31 | Fuel, Lube |  |  | 12500 |  | 12500
3 | 32 | Kill Fluids, Labor & Equipment
3 | 32 | Water & Trucking Costs |  | $/bbl | 0.5 | 10000 | 5000
3 | 34 | Fluid Disposal |  |  | 17500 |  | 17500
3 | 35 | Packer Fluid
3 | 36 | Filtration
3 | 40 | Rental Equipment |  |  |  |  | 39500 |  | 0
3 | 41 | Rentals - Surface |  |  | 34500 |  | 34500
3 | 42 | BOP Stack & Pressure Control
3 | 43 | Rotary Tools & Acc (TD, PS, RH)
3 | 44 | Fluid Related Equipment (transfer, etc)
3 | 45 | Rentals - Subsurface (pipe, BHA, etc) |  |  | 5000 |  | 5000
3 | 50 | Cementing Services |  |  |  |  | 60000 |  | 0
3 | 51 | Production Casing |  |  | 60000 |  | 60000
3 | 52 | Squeeze
3 | 53 | Plugs
3 | 60 | Wireline, Logging and Testing |  |  |  |  | 237000 |  | 0
3 | 63 | Cased Hole Logging |  |  | 50000 | 1 | 50000
3 | 64 | Transient Pressure Analysis
3 | 65 | Tracer Surveys
3 | 66 | Perforating |  |  | 12000 |  | 12000
3 | 67 | Slickline & Braided Line |  |  | 10000 |  | 10000
3 | 68 | Microseismic |  |  | 165000 |  | 165000
3 | 70 | Specialized Services |  |  |  |  | 87500 |  | 0
3 | 71 | HSE Equipment & Services |  |  | 5000 |  | 5000
3 | 72 | Welding & Fabrication |  |  | 2500 |  | 2500
3 | 73 | Torque & Test
3 | 74 | Stimulation & Sand Control
3 | 75 | Tubular Services |  |  | 30000 |  | 30000
3 | 76 | Tubular Inspection
3 | 77 | Fishing & Pipe Recovery
3 | 78 | Miscellaneous Services |  |  | 30000 |  | 30000
3 | 79 | Flowtesting |  |  | 20000 |  | 20000
3 | 80 | Transportation |  |  |  |  | 15000 |  | 0
3 | 81 | Trucking |  |  | 15000 |  | 15000
3 | 82 | Hot Shot
3 | 83 | Air
3 | 84 | Marine
3 | 110 | Admin, Insurance & Labor |  |  |  |  | 34000 |  | 0
3 | 111 | Contract Supervision, Onsite & Office |  |  | 18000 |  | 18000
3 | 112 | Contract Labor - roustabout, etc
3 | 114 | G&A Overhead |  |  | 12000 |  | 12000
3 | 115 | Payroll Labor
3 | 116 | Well Control Insurance & Services
3 | 117 | Insurance - GenLiab & Umbrella |  |  | 4000 |  | 4000
3 | 118 | LIH Fees
3 | 500 | Miscellaneous Costs - Intangible |  |  |  |  | 0 |  | 0
3 | 510 | Contingencies
3 | 520 | Accrual
CAPITALIZED TANGIBLE COSTS
Major | Minor | Definition | Description |  | Unit Cost | Qty | Total Cost | Supplement Date | Supplement Cost
3 | 1000 | Tangible Equipment |  |  |  |  | 1574034 |  | 0
3 | 1005 | Consumables - Bits, Mills, FE, Plugs | gen $2k, plugs $1.5k |  | 3500 |  | 3500
3 | 1045 | Production Casing | 9-5/8" 47# L-80 BTC |  | 98.43 | 8000 | 787440
3 | 1050 | Production Tie-Back
3 | 1055 | Production Tubing | 7" 29# L-80 BTC |  | 61.14 | 7100 | 434094
3 | 1060 | Wellhead, Tree & Fittings | SLB B-section 22k$, tree $252k |  | 284000 | 1 | 284000
3 | 1065 | Packer, Liner Hanger |  |  | 50000 | 1 | 50000
3 | 1070 | Artificial Lift Systems
3 | 1075 | Subsurface Equipment - Other |  |  | 15000 |  | 15000
3 | 1095 | Lost in Hole
3 | 1500 | Miscellaneous Costs - Tangible |  |  |  |  | 0 |  | 0
3 | 1510 | Contingencies
3 | 1520 | Accrual

## Equip
Water Oak Renewables, LLC
Operator: |  |  | Project Name
Criterion Operating, LLC |  |  | Water Oak Z031D Drill, Complete & Equip
Well Name |  |  | Field Name |  |  |  | County | State/Province | API
Water Oak Z031D |  |  | Pleasant Bayou (Frio Geothermal) |  |  |  | Brazoria | Texas
Job Category |  |  | Primary Job Description |  |  |  | Formation | Total Depth, ft MD | Well Type
Development Drilling |  |  | Equip vertical geothermal SWD |  |  |  |  | 7700 | GT SWD
AFE Number |  |  | AFE Date |  | AFE Type |  | Total CMP AFE, USD
|  |  | 2023-01-27 |  |  |  | 173000
Supplemental AFE Number |  |  | Supplement AFE Date |  | Supplement CMP AFE, USD |  | Total CMP AFE + Supplement CMP AFE, USD
[5 empty] | 0 |  | 173000
CAPITALIZED INTANGIBLE COSTS
Major | Minor | Definition | Type | Units | Unit Cost | Qty | Total Cost | Supplement Date | Supplement Cost | Comments
5 | 10 | Location Preparation |  |  |  |  | 35000 |  | 0
5 | 12 | Permitting, Regulatory |  |  | 15000 |  | 15000
5 | 14 | Road, Location, Pad Site, Foundations |  |  | 20000 |  | 20000
5 | 16 | Cleanup
5 | 17 | Containment
5 | 18 | Fire Pond, etc
5 | 30 | Fluids |  |  |  |  | 28000 |  | 0
5 | 31 | Fuel, Lube
5 | 32 | Water & Trucking Costs
5 | 34 | Fluid Disposal |  |  | 3000 |  | 3000
5 | 35 | Other |  |  | 25000 |  | 25000
5 | 36 | Filtration
5 | 40 | Rental Equipment |  |  |  |  | 5000 |  | 0
5 | 41 | Rentals - Surface |  |  | 5000 |  | 5000
5 | 42 | Crane
5 | 43 | Tools
5 | 44 | Measurement
5
5 | 70 | Specialized Services |  |  |  |  | 32500 |  | 0
5 | 71 | HSE Equipment & Services |  |  | 5000 |  | 5000
5 | 72 | Welding & Fabrication |  |  | 10000 |  | 10000
5 | 73 | Torque & Test
5 | 76 | Civil Design & Implementation
5 | 77 | Electrical Construction & Fab
5 | 78 | Mechanical Construction & Fab |  |  | 15000 |  | 15000
5 | 79 | Testing & Certification |  |  | 2500 |  | 2500
5 | 80 | Transportation |  |  |  |  | 5000 |  | 0
5 | 81 | Trucking |  |  | 5000 |  | 5000
5 | 82 | Hot Shot
5 | 83 | Air
5 | 84 | Marine
5 | 110 | Admin, Insurance & Labor |  |  |  |  | 21000 |  | 0
5 | 111 | Contract Design & Engineering |  |  | 5000 |  | 5000
5 | 112 | Contract Labor - site supervision, etc |  |  | 15000 |  | 15000
5 | 114 | G&A Overhead |  |  | 1000 |  | 1000
5 | 115 | Payroll Labor
5 | 117 | Insurance - GenLiab & Umbrella
5 | 500 | Miscellaneous Costs - Intangible |  |  |  |  | 0 |  | 0
5 | 510 | Contingencies
5 | 520 | Accrual
CAPITALIZED TANGIBLE COSTS
Major | Minor | Definition | Description |  | Unit Cost | Qty | Total Cost | Supplement Date | Supplement Cost
5 | 1000 | Tangible Equipment |  |  |  |  | 46500 |  | 0
5 | 1001 | Buildings
5 | 1002 | Cathodic Protection
5 | 1003 | Civil Installation |  |  | 3000 |  | 3000
5 | 1004 | Dehydrators
5 | 1005 | Electrical Instrumentation & Eqpmt
5 | 1006 | Emission Controls
5 | 1007 | Engines & Motors
5 | 1008 | Insulation & Painting
5 | 1009 | Measurement Equipment & Devices |  |  | 3500 |  | 3500
5 | 1010 | Mechanical Installation
5 | 1011 | Pipe, Valves & Fittings |  |  | 40000 |  | 40000
5 | 1012 | Processing Equipment & Skids
5 | 1013 | Pumps
5 | 1014 | Switchgear & Control Panels
5 | 1015 | Tanks
5 | 1016 | Telemetry Processing Equipment
5 | 1017 | Three Phase Separators
5 | 1018 | Knockouts
5 | 1019 | Turbomachinery
5 | 1020 | Environmental Control & Safety
5 | 1021
5 | 1500 | Miscellaneous Costs - Tangible |  |  |  |  | 0 |  | 0
5 | 1510 | Contingencies
5 | 1520 | Accrual

## DRL Worksheet
|  | Hole | Casing OD | Weight/Ft | Grade | Connection | Top | Bottom | Footage | Cost/Ft | Est. Cost | String Weight | Cement Volume [sks] | Mud Weight | Ft/Hr | Drilled Footage | Days Drilling | Running Pipe | Flat | Rig Days
A | Conductor | 22 | 18.625 | 85.2 | X56 |  | 0 | 100 | 100 | 0 | 0 | 8520 | 124.7625 | 8.4 | 12 | 100 | 0.34722 |  |  | 0.34722
B | Surface | 16 | 13.375 | 68 | L-80 HC | BTC | 0 | 3000 | 3000 | 85 | 255000 | 204000 | 1414.8893 | 9.5 | 150 | 2900 | 0.80556 | 1 | 0.75 | 2.5556
C | Intermediate | 12.25 | 9.625 | 47 | P-110 | mod BTC | 0 | 10500 | 10800 | 101.18 | 1092744 | 507600 | 3720.0269 | 11.5 | 75 | 7500 | 4.1667 | 1.1 | 1.2 | 6.4667
D | Drilling Liner | 8.5 | 7.625 | 29.7 | P-110 HP | SLIJ-II | 10000 | 12930 | 4900 | 70.62 | 346038 | 145530 | 453.3454 | 16.5 | 50 | 2430 | 2.025 | 1.1 | 1 | 4.125
E | Production Liner | 6.5 | 5.5 | 23 | P-110 HP | Edge SF | 12500 | 16500 | 3000 | 60.79 | 182370 | 69000 | 256.9015 | 17.5 | 17 | 3570 | 8.75 | 2 | 3 | 13.75
| Tieback |  | 5.5 | 23 | P-110 HP | VAM21/Edge SF | 0 | 6000 | 6500 | 55.7 | 362050 | 149500 | [5 empty] | 1.5 |  | 1.5
|  |  | 5.5 | 23 | P-110 HP | Edge SF | 6000 | 13800 | 8200 | 60.79 | 498478 | 188600 | [7 empty] | 0
| Coring | [17 empty] | 4 | 4
| Logging | [17 empty] | 2 | 2
[11 empty] | 2736680 | [8 empty] | 34.7444

## CMP Worksheet
Days on Location
Wellsite Prep |  | Well Prep |  | Stimulation |  | Drillout |  | Tube Up |  | Flowback
Scrape | 1.25 | NU Wellhead | 0.75 | Stages | 2 | Plugs | 2 | Packer | 0.5 | Clean-Up | 7
Cellar | 0.5 | Toe Sleeve | 0.5 | Hrs/Stg | 2 | CTDO | 2.125 | WOR | 1.25 | Well Test | 14
|  | Wet Shoe | 0.5 | Single Well | 4.3333
|  | TCP | 1 | Zipper 2 well | 4.2857
|  | Casing Test | 0.125 | Zipper 3+ | 3.2667
|  |  |  | Twin | 3.25
|  |  |  | Simulfrac | 3.25
|  |  |  | CT Sleeves | 2.2222
[10 empty] | Stand-By | 8.25
1.75 |  | 2 |  | 3 |  | 2 |  | 1.75 |  | 14 |  | Total Days | 24.5
Water Requirements
Wellsite Prep |  | Well Prep |  | Stimulation |  | Drillout |  | Tube Up |  | Flowback
|  | Wellbore Vol | 1235 | Stage Vol | 4000 | Tanks | 3 | Packer Depth | 9000
|  | Toe Sleeve | 3087.5 | Total Stim Vol | 8000 | CTDO Vol | 1200 | Tubing OD | 5.5
|  | Wet Shoe | 3087.5 | Est PD Vol | 250 |  |  | Casing ID | 8.535
|  | TCP | 1543.75 | Total PD Vol | 250 |  |  |  | 372.3956
|  | Casing Test | 123.5
0 |  | 3300 |  | 21000 |  | 1600 |  | 1000 |  | 0 |  | Total Water | 26900