## PDE (hidden)
Well Name:
API | Surface Legal Location | Field Name | Permit Number | State/Province | Well Configuration Type
Ground Elevation (ft) | Casing Flange Elevation (ft) | KB - Ground Distance (ft) | KB - Casing Flange Distance (ft) | Spud Date | Rig Release Date
Jobs
Job Category | Primary Job Type | Secondary Job Type | Start Date | End Date
Target Depth (ft-KB) |  |  | Target Formation
Objective
AFE
AFE Number | AFE Date | AFE Type | Supplemental AFE Number
Total AFE + Supplement Amount (Cost) | Total AFE Amount (Cost) |  | Total AFE Supplement Amount (Cost) |  | AFE Status
AFE Cost Breakdown
| Major Category Code | Minor Category Code | AFE Amount (Cost) | Supplement Date | Supplement Amount (Cost)

## Summary
PURE #1D Reactivation Cost Estimates
Select (x) | Description | Unrisked | Risked
x | PHASE I - Location Prep | 15197.5 | 15197.5
x | One-Time Charges | 3500 | 3500
x | PHASE II - Slickline Tag & Injection Test | 21653.1818 | 21653.1818
x | PHASE II CONTINGENCY - Coiled Tubing Clean-out | 234258.1818 | 173636.5455
x | PHASE III - Pull Tubing | 22950 | 4590
x | PHASE III CONTINGENCY - Stuck or Parted Tubing | 66900 | 6690
x | PHASE III CONTINGENCY - Tubing Replacement | 118580 | 64290
x | PHASE IV - PLUG & ABANDON | 150000 | 150000
| TOTAL | 633038.8636 | 439557.2273

## Workover
Water Oak Renewables, LLC
Operator: |  |  | Project Name
Criterion Operating, LLC |  |  | Pure #1D Workover
Well Name |  |  | Field Name |  |  |  | County | State/Province | API
Pure #1D |  |  | Martin Ranch (Frio 14,600) |  |  |  | Brazoria | Texas
Job Category |  |  | Primary Job Description |  |  |  | Formation | Total Depth, ft MD | Well Type
Workover |  |  | Reactivation |  |  |  | Frio |  | SWD
AFE Number |  |  | AFE Date |  | AFE Type |  | Total Workover AFE (RISKED), USD
|  |  | 2023-03-10 |  | Recomplete |  | 289557.2273
Total Workover AFE (UNRISKED), USD
[5 empty] | 0 |  | 289557.2273
CAPITALIZED INTANGIBLE COSTS
Major | Minor | Definition | Type | Units | Unit Cost | Qty | Total Cost | Supplement Date | Supplement Cost | Comments
4 | 10 | Location Preparation |  |  |  |  | 13500 |  | 0
4 | 12 | Permitting, Regulatory |  |  | 1000 |  | 1000
4 | 14 | Road, Location |  |  | 12500 |  | 12500
4 | 16 | Cleanup
4 | 18 | Frac Pond, Impoundment
4 | 20 | Completion Unit |  |  |  |  | 0 |  | 0
4 | 21 | Mob/Demob
4 | 22 | Completion Rig Contract | Daywork | $/day | [5 empty] | - 4 days coring; 2 days logging
4 | 25 | Coiled Tubing Unit & Support Eqpmt | Daywork | $/day | [5 empty] | - 4 days coring; 2 days logging
4 | 27 | Snubbing Unit & Support Eqpmt | Daywork | $/day | [5 empty] | - 4 days coring; 2 days logging
4 | 30 | Completion Fluids |  |  |  |  | 35000 |  | 0
4 | 31 | Fuel, Lube |  |  | 12500 |  | 12500
4 | 32 | Kill Fluids, Labor & Equipment
4 | 32 | Water & Trucking Costs |  | $/bbl | 0.5 | 10000 | 5000
4 | 34 | Fluid Disposal |  |  | 17500 |  | 17500
4 | 35 | Packer Fluid
4 | 36 | Filtration
4 | 40 | Rental Equipment |  |  |  |  | 39500 |  | 0
4 | 41 | Rentals - Surface |  |  | 34500 |  | 34500
4 | 42 | BOP Stack & Pressure Control
4 | 43 | Rotary Tools & Acc (TD, PS, RH)
4 | 44 | Fluid Related Equipment (transfer, etc)
4 | 45 | Rentals - Subsurface (pipe, BHA, etc) |  |  | 5000 |  | 5000
4 | 50 | Cementing Services |  |  |  |  | 60000 |  | 0
4 | 51 | Production Casing |  |  | 60000 |  | 60000
4 | 52 | Squeeze
4 | 53 | Plugs
4 | 60 | Wireline, Logging and Testing |  |  |  |  | 237000 |  | 0
4 | 63 | Cased Hole Logging |  |  | 50000 | 1 | 50000
4 | 64 | Transient Pressure Analysis
4 | 65 | Tracer Surveys
4 | 66 | Perforating |  |  | 12000 |  | 12000
4 | 67 | Slickline & Braided Line |  |  | 10000 |  | 10000
4 | 68 | Microseismic |  |  | 165000 |  | 165000
4 | 70 | Specialized Services |  |  |  |  | 87500 |  | 0
4 | 71 | HSE Equipment & Services |  |  | 5000 |  | 5000
4 | 72 | Welding & Fabrication |  |  | 2500 |  | 2500
4 | 73 | Torque & Test
4 | 74 | Stimulation & Sand Control
4 | 75 | Tubular Services |  |  | 30000 |  | 30000
4 | 76 | Tubular Inspection
4 | 77 | Fishing & Pipe Recovery
4 | 78 | Miscellaneous Services |  |  | 30000 |  | 30000
4 | 79 | Flowtesting |  |  | 20000 |  | 20000
4 | 80 | Transportation |  |  |  |  | 15000 |  | 0
4 | 81 | Trucking |  |  | 15000 |  | 15000
4 | 82 | Hot Shot
4 | 83 | Air
4 | 84 | Marine
4 | 110 | Admin, Insurance & Labor |  |  |  |  | 34000 |  | 0
4 | 111 | Contract Supervision, Onsite & Office |  |  | 18000 |  | 18000
4 | 112 | Contract Labor - roustabout, etc
4 | 114 | G&A Overhead |  |  | 12000 |  | 12000
4 | 115 | Payroll Labor
4 | 116 | Well Control Insurance & Services
4 | 117 | Insurance - GenLiab & Umbrella |  |  | 4000 |  | 4000
4 | 118 | LIH Fees
4 | 500 | Miscellaneous Costs - Intangible |  |  |  |  | 0 |  | 0
4 | 510 | Contingencies
4 | 520 | Accrual
CAPITALIZED TANGIBLE COSTS
Major | Minor | Definition | Description |  | Unit Cost | Qty | Total Cost | Supplement Date | Supplement Cost
4 | 1000 | Tangible Equipment |  |  |  |  | 1574034 |  | 0
4 | 1005 | Consumables - Bits, Mills, FE, Plugs | gen $2k, plugs $1.5k |  | 3500 |  | 3500
4 | 1045 | Production Casing | 9-5/8" 47# L-80 BTC |  | 98.43 | 8000 | 787440
4 | 1050 | Production Tie-Back
4 | 1055 | Production Tubing | 7" 29# L-80 BTC |  | 61.14 | 7100 | 434094
4 | 1060 | Wellhead, Tree & Fittings | SLB B-section 22k$, tree $252k |  | 284000 | 1 | 284000
4 | 1065 | Packer, Liner Hanger |  |  | 50000 | 1 | 50000
4 | 1070 | Artificial Lift Systems
4 | 1075 | Subsurface Equipment - Other |  |  | 15000 |  | 15000
4 | 1095 | Lost in Hole
4 | 1500 | Miscellaneous Costs - Tangible |  |  |  |  | 0 |  | 0
4 | 1510 | Contingencies
4 | 1520 | Accrual
Major | Minor | Definition | Units | Unit Cost | Qty | Probability | RISKED Total Cost | UNRISKED Total Cost
|  | PHASE I - Location Prep |  |  |  |  | 15197.5 | 15197.5
|  | Lease Crew | $/hr | 355 | 10 |  | 3550 | 3550
|  | Location Work | flat |  |  |  | 0 | 0
|  | Cattle Guard Fabrication | flat |  |  |  | 0 | 0
|  | Set Anchors | flat | 5000 | 1 |  | 5000 | 5000
|  | Wellhead tech |  | 2000 | 1 |  | 2000 | 2000
|  | Torque & Test |  | 1700 | 1 |  | 1700 | 1700
|  | Kill Truck | $/hr | 150 | 8 |  | 1200 | 1200
|  | Vacuum Trucks | $/hr | 125 | 8 |  | 1000 | 1000
|  | Water | $/bbl | 1.25 | 110 |  | 137.5 | 137.5
|  | Disposal | $/bbl | 1 | 110 |  | 110 | 110
|  | Supervision | $/day | 500 | 1 |  | 500 | 500
0
|  | Spread Cost |  |  |  |  | 4030 | 4030
|  | Open Top Tanks | $/day | 150 | 1 |  | 150 | 150
|  | Frac Tanks | $/day | 65 | 2 |  | 130 | 130
|  | Gate Guard | $/day | 250 | 1 |  | 250 | 250
|  | Flowback Equipment | $/day | 3000 | 1 |  | 3000 | 3000
|  | Safety Equipment | $/day | 500 | 1 |  | 500 | 500
|  | One-Time Charges |  |  |  |  | 3500 | 3500
|  | Rig Mob and Demob |  |  |  |  | 0 | 0
|  | T,G,LP,F,M,T,TT,OTT,FT,FBE delivery & pick-up |  | 3500 | 1 |  | 3500 | 3500
|  | Equipment inspection & damages |  |  |  |  | 0 | 0
|  | PHASE II - Slickline Tag & Injection Test |  |  |  |  | 21653.1818 | 21653.1818
|  | Spread | $/day | 4030 | 2 |  | 8060 | 8060
|  | Kill Truck | $/hr | 150 | 10 |  | 1500 | 1500
|  | Vacuum Trucks | $/hr | 125 | 14.5455 |  | 1818.1818 | 1818.1818 |  |  | Depth | 14500
|  | Water | $/bbl | 1.25 | 200 |  | 250 | 250 |  |  | Depth | 14500
|  | Disposal | $/bbl | 1 | 200 |  | 200 | 200 |  |  | pore press | 0.7
|  | Slickline | $/day | 5325 | 1 |  | 5325 | 5325 |  |  | BHP | 10150
|  | Wellhead Tech |  | 2000 | 1 |  | 2000 | 2000 |  |  | Req MW | 13.4615
|  | Supervision | $/day | 1250 | 2 |  | 2500 | 2500 |  |  | 3.5 12.95 |  | 2.992 | 0.0086956 | 3354 | 29.1651
[14 empty] | 0 |  | 0
[11 empty] | 5.500 9.3 |  | 5.012 | 0.024401 | 79 | 1.9276 | to btm perf
|  | PHASE II CONTINGENCY - Coiled Tubing Clean-out |  |  |  |  | 173636.5455 | 234258.1818 |  |  | 7.625 39 |  | 6.625 | 0.042633
[11 empty] | 5.500 x 3.500 |  |  | 0.012501 | 3354 | 41.9299 |  | Inside | 31.0928 | bbls
|  | Spread | $/day | 4030 | 3 | 80% | 9672 | 12090 |  |  | 7.625 x 3.500 |  |  | 0.030734 |  | 0 |  | Outside | 41.9299 | bbls
|  | Coiled Tubing Unit (2-3/8") | $/day | 45200 | 3 | 80% | 108480 | 135600 |  |  | 7.625 x 5.000 |  |  | 0.018349 |  | 0 |  |  | 73.0227
|  | BHA | $/job | 12500 | 3 | 80% | 30000 | 37500
|  | Chemicals | $/job | 5000 | 3 | 80% | 12000 | 15000
|  | Torque & Test | $/job | 1700 | 3 | 80% | 4080 | 5100
|  | Vacuum Trucks | $/hr | 125 | 14.5455 | 80% | 1454.5455 | 1818.1818
|  | Water | $/bbl | 1.25 | 200 | 80% | 200 | 250
|  | Disposal | $/bbl | 1 | 200 | 80% | 160 | 200
|  | Supervision | $/day | 1250 | 3 | 80% | 3000 | 3750
|  | PHASE III - Pull Tubing |  |  |  |  | 4590 | 22950
|  | Spread | $/day | 4030 | 1 | 20% | 806 | 4030
|  | Workover Rig | $/14hr | 6370 | 1 | 20% | 1274 | 6370
|  | Rig Crew Travel | $/hr | 200 | 8 | 20% | 320 | 1600
|  | Per Diem & Lodging | $/day | 1000 | 1 | 20% | 200 | 1000
|  | BOP Stack | $/day | 5000 | 1 | 20% | 1000 | 5000
|  | Torque & Test | $/job | 1700 | 1 | 20% | 340 | 1700
|  | Wellhead Tech |  | 2000 | 1 | 20% | 400 | 2000
|  | Supervision | $/day | 1250 | 1 | 20% | 250 | 1250
|  | PHASE III CONTINGENCY - Stuck or Parted Tubing |  |  |  |  | 6690 | 66900
|  | Spread | $/day | 4030 | 2 | 10% | 806 | 8060
|  | Workover Rig | $/14hr | 6370 | 2 | 10% | 1274 | 12740
|  | Rig Crew Travel | $/hr | 200 | 3 | 10% | 60 | 600
|  | Per Diem & Lodging | $/day | 1000 | 2 | 10% | 200 | 2000
|  | BOP Stack | $/day | 5000 | 2 | 10% | 1000 | 10000
|  | Fishing Tools, Supv | $/day | 15000 | 2 | 10% | 3000 | 30000
|  | Workstring | $/ft-day | 0.16667 | 6000 | 10% | 100 | 1000
|  | Supervision | $/day | 1250 | 2 | 10% | 250 | 2500
|  | PHASE III CONTINGENCY - Tubing Replacement |  |  |  |  | 64290 | 118580
|  | Spread | $/day | 4030 | 1 | 50% | 2015 | 4030
|  | Tubing Inspection Log |  | 20000 | 1 | 75% | 15000 | 20000
|  | Workover Rig | $/day | 200 | 1 | 50% | 100 | 200
|  | Rig Crew Travel | $/hr | 200 | 3 | 50% | 300 | 600
|  | Per Diem & Lodging | $/day | 1000 | 1 | 50% | 500 | 1000
|  | BOP Stack | $/day | 5000 | 1 | 50% | 2500 | 5000
|  | 3-1/2" 9.3# N-80 tubing | $/ft | 19 | 3500 | 50% | 33250 | 66500
|  | Packer |  | 20000 | 1 | 50% | 10000 | 20000
|  | Supervision | $/day | 1250 | 1 | 50% | 625 | 1250