## Gantt
Engineering Project Management Dashboard
[22 empty] | Project Timespan: | [7 empty] | 2022-12-12 |  |  |  | - | 2024-06-03 |  |  |  | (539) | [22 empty] | Settings
Scroll Forward
|  | Input Column | [6 empty] | Auto Stage ind.start |  | =MIN(ITEMS_START) | [10 empty] | Color By | [9 empty] | Display | [8 empty] | Show Progress | [7 empty] | Time Scale | [12 empty] | Highlight
|  | Calculated Column | [6 empty] | Auto Stage workdays |  | =MAX(ITEMS_END)-plan_start | [10 empty] | Project Structure | [9 empty] | Plan | [8 empty] | No | [7 empty] | Weekly | [12 empty] | Today
|  | Snapshot Column | [6 empty] | Auto Stage % |  | =SUM(ITEMS_PERCENT*ITEMS_WORKDAYS)/SUM(ITEMS_WORKDAYS)
| **Chart uses a 7-day work week | [8 empty] | copy this formula into a type "S" in workdays column ONLY!
| Unicode Icons | [7 empty] | Actual Plan | [9 empty] | Base Plan |  | Today | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-17 | 2024-06-24 | 2024-07-01 | 2024-07-08 | 2024-07-15 | 2024-07-22 | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22
| ⚠ - ◆ - ⚑ - ↖ - ↙ | [7 empty] | Updated on: | [9 empty] | Saved on: |  | 0
| ids |  |  | Item Details |  |  |  |  | 2023-01-02 | [9 empty] | 2023-01-02
| id | s id | r id | Type | Description | Role | Team Member | ⚠ | ind. Start | ind. End | d. id | d. Item |  | d. conn | d. lag | Work days | Start | End | Start | End | % | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M
| 1 | 1 | -1 | S | Data Gathering |  |  |  | 2023-01-09 |  |  |  |  | FS |  | 350 | Start: 2023-01-09; End: 2023-12-24; 2023-01-02 Start: 2023-01-09; 2023-01-02 End: 2023-12-24; 2023-01-02 %: 0%
| 2 | 1 | -1 | T | Seismic Interpretation |  |  |  | 2023-01-09 |  |  |  |  | FS |  | 51 | Start: 2023-01-09; End: 2023-02-28; 2023-01-02 Start: 2023-01-09; 2023-01-02 End: 2023-02-28
| 3 | 1 | -1 | T | Geologic Model | [5 empty] | 2 | ↖ | (T) Seismic… | FS |  | 14 | Start: 2023-03-01; End: 2023-03-14; 2023-01-02 Start: 2023-03-01; 2023-01-02 End: 2023-03-14
| 4 | 1 | -1 | T | Reservoir Model | [5 empty] | 3 | ↖ | (T) Geologi… | FS |  | 14 | Start: 2023-03-15; End: 2023-03-28; 2023-01-02 Start: 2023-03-15; 2023-01-02 End: 2023-03-28
| 5 | 1 | -1 | T | - Well Spacing/Temp/Rate Model - 20MW | [5 empty] | 4 | ↖ | (T) Reservo… | FS |  | 30 | Start: 2023-03-29; End: 2023-04-27; 2023-01-02 Start: 2023-03-29; 2023-01-02 End: 2023-04-27
| 6 | 1 | -1 | T | - 20MW Full Simulation | [5 empty] | 5 | ↖ | (T) - Well … | FS |  | 30 | Start: 2023-04-28; End: 2023-05-27; 2023-01-02 Start: 2023-04-28; 2023-01-02 End: 2023-05-27
| 7 | 1 | -1 | T | - 20MW Development Plan | [5 empty] | 6 | ↖ | (T) - 20MW … | SS | 5 | 60 | Start: 2023-05-03; End: 2023-07-01; 2023-01-02 Start: 2023-05-03; 2023-01-02 End: 2023-07-01
| 8 | 1 | -1 | T | Core Analysis - Water Oak 1 P011 | [5 empty] | 42 | ↙ | (T) Drill &… | SS | 30 | 60 | Start: 2023-07-21; End: 2023-09-18; 2023-01-02 Start: 2023-07-21; 2023-01-02 End: 2023-09-18
| 9 | 1 | -1 | T | Reservoir Test Analysis - Water Oak D031 | [5 empty] | 41 | ↙ | (T) Injecti… | SS | 5 | 75 | Start: 2023-07-31; End: 2023-10-13; 2023-01-02 Start: 2023-07-31; 2023-01-02 End: 2023-10-13
| 10 | 1 | -1 | T | Reservoir Test Analysis - Water Oak 1 P011 | [5 empty] | 45 | ↙ | (T) Flow Te… | SS | 5 | 75 | Start: 2023-10-12; End: 2023-12-25; 2023-01-02 Start: 2023-10-12; 2023-01-02 End: 2023-12-25
| 11 | 2 | -1 | S | PURE #1 ACTIVITIES |  |  |  | 2022-12-12 |  |  |  |  | FS |  | 139 | Start: 2022-12-12; End: 2023-04-29; 2023-01-02 Start: 2022-12-12; 2023-01-02 End: 2023-04-29; 2023-01-02 %: 11.95%
| 12 | 2 | -1 | T | Acquisition |  |  |  | 2022-12-12 | 2023-01-31 |  |  |  | SS | -10 | 35 | Start: 2022-12-12; End: 2023-01-15; 2023-01-02 Start: 2022-12-12; 2023-01-02 End: 2023-01-15; 2023-01-02 %: 70%
| 13 | 2 | -1 | T | SUA & Damages |  |  | ⚠ |  |  | 12 | ↖ | (T) Acquisi… | FS | -10 | 30 | Start: 2023-01-06; End: 2023-02-04; 2023-01-02 Start: 2023-01-06; 2023-01-02 End: 2023-02-04
| 14 | 2 | -1 | T | Surface Site Prep | [5 empty] | 13 | ↖ | (T) SUA & D… | FS |  | 30 | Start: 2023-02-05; End: 2023-03-06; 2023-01-02 Start: 2023-02-05; 2023-01-02 End: 2023-03-06
| 15 | 2 | -1 | T | Conversion CWOP | [5 empty] | 13 | ↖ | (T) SUA & D… | SS |  | 31 | Start: 2023-01-06; End: 2023-02-05; 2023-01-02 Start: 2023-01-06; 2023-01-02 End: 2023-02-05; 2023-01-02 %: 10%
| 16 | 2 | -1 | T | Permitting | [5 empty] | 12 | ↖ | (T) Acquisi… | FS |  | 91 | Start: 2023-01-16; End: 2023-04-16; 2023-01-02 Start: 2023-01-16; 2023-01-02 End: 2023-04-16
| 17 | 2 | -1 | T | Workover & Testing | [5 empty] | 16 | ↖ | (T) Permitt… | FS |  | 14 | Start: 2023-04-17; End: 2023-04-30; 2023-01-02 Start: 2023-04-17; 2023-01-02 End: 2023-04-30
| 18 | 3 | -1 | S | PURE #1D ACTIVITIES |  |  |  | 2022-12-12 |  |  |  |  | FF |  | 539 | Start: 2022-12-12; End: 2024-06-02; 2023-01-02 Start: 2022-12-12; 2023-01-02 End: 2024-06-02; 2023-01-02 %: 9.423%
| 19 | 3 | -1 | T | Acquisition | [5 empty] | 12 | ↖ | (T) Acquisi… | SS |  | 35 | Start: 2022-12-12; End: 2023-01-15; 2023-01-02 Start: 2022-12-12; 2023-01-02 End: 2023-01-15; 2023-01-02 %: 70%
| 20 | 3 | -1 | T | Surface Site Prep, Facilities Repair & Inj Tests | [5 empty] | 14 | ↖ | (T) Surface… | SS |  | 30 | Start: 2023-02-05; End: 2023-03-06; 2023-01-02 Start: 2023-02-05; 2023-01-02 End: 2023-03-06
| 21 | 3 | -1 | T | Workover & Remediation | [5 empty] | 17 | ↖ | (T) Workove… | FS |  | 14 | Start: 2023-05-01; End: 2023-05-14; 2023-01-02 Start: 2023-05-01; 2023-01-02 End: 2023-05-14
| 22 | 3 | -1 | T | Disposal Operations | [5 empty] | 45 | ↙ | (T) Flow Te… | SS |  | 91 | Start: 2023-10-07; End: 2024-01-05; 2023-01-02 Start: 2023-10-07; 2023-01-02 End: 2024-01-05
| 23 | 3 | -1 | T | Surface Equipment Removal | [5 empty] | 22 | ↖ | (T) Disposa… | FS | 60 | 90 | Start: 2024-03-06; End: 2024-06-03; 2023-01-02 Start: 2024-03-06; 2023-01-02 End: 2024-06-03
| 24 | 4 | -1 | S | WATER OAK 1 PHASE I DEVELOPMENT |  |  |  | 2022-12-12 |  |  |  |  | FS |  | 388 | Start: 2022-12-12; End: 2024-01-03; 2023-01-02 Start: 2022-12-12; 2023-01-02 End: 2024-01-03; 2023-01-02 %: 7.563%
| 25 | 4 | -1 | T | OCTG Order |  |  |  | 2022-12-12 |  |  |  |  | FS |  | 12 | Start: 2022-12-12; End: 2022-12-23; 2023-01-02 Start: 2022-12-12; 2023-01-02 End: 2022-12-23; 2023-01-02 %: 100%
| 26 | 4 | -1 | T | Internal coating for production casing | [5 empty] | 25 | ↖ | (T) OCTG Or… | FS | 81 | 56 | Start: 2023-03-15; End: 2023-05-09; 2023-01-02 Start: 2023-03-15; 2023-01-02 End: 2023-05-09; 2023-01-02 %: 5%
| 27 | 4 | -1 | T | Wellhead Order |  |  |  | 2022-12-16 |  |  |  |  | SS |  | 22 | Start: 2022-12-16; End: 2023-01-06; 2023-01-02 Start: 2022-12-16; 2023-01-02 End: 2023-01-06; 2023-01-02 %: 90%
| 28 | 4 | -1 | T | Land Work, SUA & Damages |  |  | ⚠ | 2023-02-01 |  |  |  |  | FS |  | 30 | Start: 2023-02-01; End: 2023-03-02; 2023-01-02 Start: 2023-02-01; 2023-01-02 End: 2023-03-02
| 29 | 4 | -1 | T | Well Staking and Plats |  |  |  | 2022-12-20 |  |  |  |  | FS |  | 18 | Start: 2022-12-20; End: 2023-01-06; 2023-01-02 Start: 2022-12-20; 2023-01-02 End: 2023-01-06; 2023-01-02 %: 90%
| 30 | 4 | -1 | T | Environmental Survey & Report |  |  |  | 2022-12-20 |  |  |  |  | FS |  | 28 | Start: 2022-12-20; End: 2023-01-16; 2023-01-02 Start: 2022-12-20; 2023-01-02 End: 2023-01-16; 2023-01-02 %: 50%
| 31 | 4 | -1 | T | Permitting Process |  |  | ⚠ |  |  | 29 | ↖ | (T) Well St… | FS |  | 10 | Start: 2023-01-07; End: 2023-01-16; 2023-01-02 Start: 2023-01-07; 2023-01-02 End: 2023-01-16; 2023-01-02 %: 10%
| 32 | 4 | -1 | T | Permit Approval Time (WO 1 P011) | [5 empty] | 31 | ↖ | (T) Permitt… | FS |  | 14 | Start: 2023-01-17; End: 2023-01-30; 2023-01-02 Start: 2023-01-17; 2023-01-02 End: 2023-01-30
| 33 | 4 | -1 | T | Permit Approval Time (WO 1 D031) | [5 empty] | 31 | ↖ | (T) Permitt… | FS |  | 100 | Start: 2023-01-17; End: 2023-04-26; 2023-01-02 Start: 2023-01-17; 2023-01-02 End: 2023-04-26
| 34 | 4 | -1 | T | Drilling RFP's (pad, roads, mud, bits, cmt, etc) |  |  | ⚠ | 2023-01-03 |  |  |  |  | FS |  | 60 | Start: 2023-01-03; End: 2023-03-03; 2023-01-02 Start: 2023-01-03; 2023-01-02 End: 2023-03-03
| 35 | 4 | -1 | T | Compl RFP's (rig, WL, pkr, PCE, test) |  |  | ⚠ | 2023-01-03 |  |  |  |  | FS |  | 60 | Start: 2023-01-03; End: 2023-03-03; 2023-01-02 Start: 2023-01-03; 2023-01-02 End: 2023-03-03
| 36 | 4 | -1 | T | Pad Construction & Conductors |  |  |  | 2023-03-01 |  |  |  |  | FS |  | 70 | Start: 2023-03-01; End: 2023-05-09; 2023-01-02 Start: 2023-03-01; 2023-01-02 End: 2023-05-09
| 37 | 4 | -1 | T | Final Drill Plans and DWOP's |  |  | ⚠ |  |  | 36 | ↖ | (T) Pad Con… | SS |  | 60 | Start: 2023-03-01; End: 2023-04-29; 2023-01-02 Start: 2023-03-01; 2023-01-02 End: 2023-04-29
| 38 | 4 | -1 | T | Drilling Operations, WO D031 |  |  |  | 2023-05-15 |  |  |  |  | FS | 7 | 30 | Start: 2023-05-15; End: 2023-06-13; 2023-01-02 Start: 2023-05-15; 2023-01-02 End: 2023-06-13
| 39 | 4 | -1 | T | Completion Planning & CWOP, WO D031 | [5 empty] | 38 | ↖ | (T) Drillin… | FS |  | 14 | Start: 2023-06-14; End: 2023-06-27; 2023-01-02 Start: 2023-06-14; 2023-01-02 End: 2023-06-27
| 40 | 4 | -1 | T | Completion Operations, WO D031 | [5 empty] | 39 | ↖ | (T) Complet… | FS | 7 | 21 | Start: 2023-07-05; End: 2023-07-25; 2023-01-02 Start: 2023-07-05; 2023-01-02 End: 2023-07-25
| 41 | 4 | -1 | T | Injection Testing & PTA, WO D031 | [5 empty] | 40 | ↖ | (T) Complet… | FS |  | 28 | Start: 2023-07-26; End: 2023-08-22; 2023-01-02 Start: 2023-07-26; 2023-01-02 End: 2023-08-22
| 42 | 4 | -1 | T | Drill & Core Operations, WO 1 P011 | [5 empty] | 38 | ↖ | (T) Drillin… | FS | 7 | 45 | Start: 2023-06-21; End: 2023-08-04; 2023-01-02 Start: 2023-06-21; 2023-01-02 End: 2023-08-04
| 43 | 4 | -1 | T | Completion Planning & CWOP, WO 1 P011 | [5 empty] | 42 | ↖ | (T) Drill &… | FS | 14 | 14 | Start: 2023-08-19; End: 2023-09-01; 2023-01-02 Start: 2023-08-19; 2023-01-02 End: 2023-09-01
| 44 | 4 | -1 | T | Completion Operations, WO 1 P011 | [5 empty] | 43 | ↖ | (T) Complet… | FS | 7 | 28 | Start: 2023-09-09; End: 2023-10-06; 2023-01-02 Start: 2023-09-09; 2023-01-02 End: 2023-10-06
| 45 | 4 | -1 | T | Flow Testing & PTA, WO 1 P011 | [5 empty] | 44 | ↖ | (T) Complet… | FS |  | 60 | Start: 2023-10-07; End: 2023-12-05; 2023-01-02 Start: 2023-10-07; 2023-01-02 End: 2023-12-05
| 46 | 4 | -1 | T | Make Power | [5 empty] | 45 | ↖ | (T) Flow Te… | SS |  | 90 | Start: 2023-10-07; End: 2024-01-04; 2023-01-02 Start: 2023-10-07; 2023-01-02 End: 2024-01-04
| 47 | 5 | -1 | S | FACILITIES CONSTRUCTION |  |  |  | 2023-03-22 |  |  |  |  | FS |  | 193 | Start: 2023-03-22; End: 2023-09-30; 2023-01-02 Start: 2023-03-22; 2023-01-02 End: 2023-09-30; 2023-01-02 %: 0.3784%
| 48 | 5 | -1 | T | Spec & Order Surface Facilities for Phase I |  |  | ⚠ |  |  | 50 | ↙ | (T) Equip W… | SF | -84 | 14 | Start: 2023-03-22; End: 2023-04-04; 2023-01-02 Start: 2023-03-22; 2023-01-02 End: 2023-04-04; 2023-01-02 %: 5%
| 49 | 5 | -1 | T | Gas Marketing Agreement |  |  | ⚠ |  |  | 48 | ↖ | (T) Spec & … | SS |  | 30 | Start: 2023-03-22; End: 2023-04-20; 2023-01-02 Start: 2023-03-22; 2023-01-02 End: 2023-04-20
| 50 | 5 | -1 | T | Equip Water Oak D031 | [5 empty] | 40 | ↖ | (T) Complet… | SS | -7 | 21 | Start: 2023-06-28; End: 2023-07-18; 2023-01-02 Start: 2023-06-28; 2023-01-02 End: 2023-07-18
| 51 | 5 | -1 | T | Equip Water Oak 1 P011 | [5 empty] | 44 | ↖ | (T) Complet… | SS | -7 | 30 | Start: 2023-09-02; End: 2023-10-01; 2023-01-02 Start: 2023-09-02; 2023-01-02 End: 2023-10-01
| 52 | 5 | -1 | T | W/G Prod and Inj Line Installation | [5 empty] | 45 | ↖ | (T) Flow Te… | SF | -14 | 90 | Start: 2023-06-25; End: 2023-09-22; 2023-01-02 Start: 2023-06-25; 2023-01-02 End: 2023-09-22
| 53 | 6 | -1 | S | CYMRIC 1MW ORC |  |  |  | 2023-01-16 |  |  |  |  | FS |  | 353 | Start: 2023-01-16; End: 2024-01-03; 2023-01-02 Start: 2023-01-16; 2023-01-02 End: 2024-01-03; 2023-01-02 %: 2.389%
| 54 | 6 | -1 | T | Survey & Permitting |  |  | ⚠ | 2023-01-16 |  |  |  |  | FS |  | 60 | Start: 2023-01-16; End: 2023-03-16; 2023-01-02 Start: 2023-01-16; 2023-01-02 End: 2023-03-16; 2023-01-02 %: 25%
| 55 | 6 | -1 | T | Identify Shop for Repair, Refurb & Shop Test |  |  | ⚠ | 2023-02-01 |  |  |  |  | SS |  | 30 | Start: 2023-02-01; End: 2023-03-02; 2023-01-02 Start: 2023-02-01; 2023-01-02 End: 2023-03-02
| 56 | 6 | -1 | T | SUA & Damages |  |  | ⚠ |  |  | 28 | ↖ | (T) Land Wo… | SS |  | 30 | Start: 2023-02-01; End: 2023-03-02; 2023-01-02 Start: 2023-02-01; 2023-01-02 End: 2023-03-02
| 57 | 6 | -1 | T | Transmission Design & Integration Plan |  |  | ⚠ | 2023-02-01 |  |  |  |  | SS |  | 90 | Start: 2023-02-01; End: 2023-05-01; 2023-01-02 Start: 2023-02-01; 2023-01-02 End: 2023-05-01
| 58 | 6 | -1 | T | Construct Pad and Civil Works |  |  | ⚠ |  |  | 36 | ↖ | (T) Pad Con… | SS |  | 90 | Start: 2023-03-01; End: 2023-05-29; 2023-01-02 Start: 2023-03-01; 2023-01-02 End: 2023-05-29
| 59 | 6 | -1 | T | Transport to Texas Repair & Refurb |  |  | ⚠ |  |  | 60 | ↙ | (T) Repairs… | SF | -7 | 14 | Start: 2023-03-22; End: 2023-04-04; 2023-01-02 Start: 2023-03-22; 2023-01-02 End: 2023-04-04
| 60 | 6 | -1 | T | Repairs & Refurbishment | [5 empty] | 61 | ↙ | (T) Move OR… | SF | -7 | 90 | Start: 2023-04-12; End: 2023-07-10; 2023-01-02 Start: 2023-04-12; 2023-01-02 End: 2023-07-10
| 61 | 6 | -1 | T | Move ORC to Pad | [5 empty] | 63 | ↙ | (T) Testing… | SF | -14 | 14 | Start: 2023-07-18; End: 2023-07-31; 2023-01-02 Start: 2023-07-18; 2023-01-02 End: 2023-07-31
| 62 | 6 | -1 | T | Transmission Line Construction | [5 empty] | 63 | ↙ | (T) Testing… | FF | -14 | 60 | Start: 2023-07-02; End: 2023-08-30; 2023-01-02 Start: 2023-07-02; 2023-01-02 End: 2023-08-30
| 63 | 6 | -1 | T | Testing & Commissioning | [5 empty] | 64 | ↙ | (T) Connect… | SF | 7 | 30 | Start: 2023-08-15; End: 2023-09-13; 2023-01-02 Start: 2023-08-15; 2023-01-02 End: 2023-09-13
| 64 | 6 | -1 | T | Connection/Integration | [5 empty] | 65 | ↙ | (T) Power D… | SF |  | 30 | Start: 2023-09-07; End: 2023-10-06; 2023-01-02 Start: 2023-09-07; 2023-01-02 End: 2023-10-06
| 65 | 6 | -1 | T | Power Delivery & Sales | [5 empty] | 46 | ↖ | (T) Make Po… | FF |  | 90 | Start: 2023-10-07; End: 2024-01-04; 2023-01-02 Start: 2023-10-07; 2023-01-02 End: 2024-01-04
| 66 | 7 | -1 | S | PHASE II DEVELOPMENT |  |  |  | 2023-05-03 |  |  |  |  | FS |  | 978 | Start: 2023-05-03; End: 2026-01-04; 2023-01-02 %: 0%
| 67 | 7 | -1 | T | Land/Lease | [5 empty] | 7 | ↖ | (T) - 20MW … | SS |  | 60 | Start: 2023-05-03; End: 2023-07-01
| 68 | 7 | -1 | T | SUA & Damages | [5 empty] | 67 | ↖ | (T) Land/Le… | FS | -30 | 60 | Start: 2023-06-02; End: 2023-07-31
| 69 | 7 | -1 | T | Permitting | [5 empty] | 67 | ↖ | (T) Land/Le… | FS | -30 | 180 | Start: 2023-06-02; End: 2023-11-28
| 70 | 7 | -1 | T | Order Tubulars & Wellheads | [5 empty] | 7 | ↖ | (T) - 20MW … | FS |  | 270 | Start: 2023-07-02; End: 2024-03-27
| 71 | 7 | -1 | T | Order Surface Facilities for 22 thru 92 | [5 empty] | 7 | ↖ | (T) - 20MW … | FS |  | 270 | Start: 2023-07-02; End: 2024-03-27
| 72 | 7 | -1 | T | Well Plans & DWOP | [5 empty] | 69 | ↖ | (T) Permitt… | FS | -45 | 120 | Start: 2023-10-15; End: 2024-02-11
| 73 | 7 | -1 | T | Pad & Cond - WO1 P022, P032, N042, N052 | [5 empty] | 69 | ↖ | (T) Permitt… | FS | -10 | 60 | Start: 2023-11-19; End: 2024-01-17
| 74 | 7 | -1 | T | P022 Drill WO1 | [5 empty] | 70 | ↖ | (T) Order T… | FS | 14 | 45 | Start: 2024-04-11; End: 2024-05-25
| 75 | 7 | -1 | T | P022 Complete WO1 | [5 empty] | 74 | ↖ | (T) P022 Dr… | FS | 10 | 30 | Start: 2024-06-05; End: 2024-07-04
| 76 | 7 | -1 | T | P022 Equip WO1 | [5 empty] | 75 | ↖ | (T) P022 Co… | SS |  | 30 | Start: 2024-06-05; End: 2024-07-04
| 77 | 7 | -1 | T | P032 Drill WO1 | [5 empty] | 74 | ↖ | (T) P022 Dr… | FS | 7 | 45 | Start: 2024-06-02; End: 2024-07-16
| 78 | 7 | -1 | T | P032 Complete WO1 | [5 empty] | 77 | ↖ | (T) P032 Dr… | FS | 10 | 30 | Start: 2024-07-27; End: 2024-08-25
| 79 | 7 | -1 | T | P032 Equip WO1 | [5 empty] | 78 | ↖ | (T) P032 Co… | SS |  | 30 | Start: 2024-07-27; End: 2024-08-25
| 80 | 7 | -1 | T | N042 Drill WO1 | [5 empty] | 77 | ↖ | (T) P032 Dr… | FS | 7 | 45 | Start: 2024-07-24; End: 2024-09-06
| 81 | 7 | -1 | T | N042 Complete WO1 | [5 empty] | 80 | ↖ | (T) N042 Dr… | FS | 10 | 30 | Start: 2024-09-17; End: 2024-10-16
| 82 | 7 | -1 | T | N042 Equip WO1 | [5 empty] | 81 | ↖ | (T) N042 Co… | SS |  | 30 | Start: 2024-09-17; End: 2024-10-16
| 83 | 7 | -1 | T | NO52 Drill WO1 | [5 empty] | 80 | ↖ | (T) N042 Dr… | FS | 7 | 45 | Start: 2024-09-14; End: 2024-10-28
| 84 | 7 | -1 | T | NO52 Complete WO1 | [5 empty] | 83 | ↖ | (T) NO52 Dr… | FS | 10 | 30 | Start: 2024-11-08; End: 2024-12-07
| 85 | 7 | -1 | T | NO52 Equip WO1 | [5 empty] | 84 | ↖ | (T) NO52 Co… | SS |  | 30 | Start: 2024-11-08; End: 2024-12-07
| 86 | 7 | -1 | T | Pad & Cond - WO1 P062, P072, N082, N092 | [5 empty] | 83 | ↖ | (T) NO52 Dr… | SF | -14 | 60 | Start: 2024-07-02; End: 2024-08-30
| 87 | 7 | -1 | T | P062 Drill | [5 empty] | 83 | ↖ | (T) NO52 Dr… | FS | 7 | 45 | Start: 2024-11-05; End: 2024-12-19
| 88 | 7 | -1 | T | P062 Complete | [5 empty] | 87 | ↖ | (T) P062 Dr… | FS | 10 | 30 | Start: 2024-12-30; End: 2025-01-28
| 89 | 7 | -1 | T | P062 Equip | [5 empty] | 88 | ↖ | (T) P062 Co… | FS |  | 30 | Start: 2025-01-29; End: 2025-02-27
| 90 | 7 | -1 | T | P072 Drill | [5 empty] | 87 | ↖ | (T) P062 Dr… | FS | 7 | 45 | Start: 2024-12-27; End: 2025-02-09
| 91 | 7 | -1 | T | P072 Complete | [5 empty] | 90 | ↖ | (T) P072 Dr… | FS | 10 | 30 | Start: 2025-02-20; End: 2025-03-21
| 92 | 7 | -1 | T | P072 Equip | [5 empty] | 91 | ↖ | (T) P072 Co… | FS |  | 30 | Start: 2025-03-22; End: 2025-04-20
| 93 | 7 | -1 | T | N082 Drill | [5 empty] | 90 | ↖ | (T) P072 Dr… | FS | 7 | 45 | Start: 2025-02-17; End: 2025-04-02
| 94 | 7 | -1 | T | N082 Complete | [5 empty] | 93 | ↖ | (T) N082 Dr… | FS | 10 | 30 | Start: 2025-04-13; End: 2025-05-12
| 95 | 7 | -1 | T | N082 Equip | [5 empty] | 94 | ↖ | (T) N082 Co… | FS |  | 30 | Start: 2025-05-13; End: 2025-06-11
| 96 | 7 | -1 | T | N092 Drill | [5 empty] | 93 | ↖ | (T) N082 Dr… | FS | 7 | 45 | Start: 2025-04-10; End: 2025-05-24
| 97 | 7 | -1 | T | N092 Complete | [5 empty] | 96 | ↖ | (T) N092 Dr… | FS | 10 | 30 | Start: 2025-06-04; End: 2025-07-03
| 98 | 7 | -1 | T | N092 Equip | [5 empty] | 97 | ↖ | (T) N092 Co… | FS |  | 30 | Start: 2025-07-04; End: 2025-08-02
| 99 | 7 | -1 | T | Conductor - WO1 N101, P111, N121 | [5 empty] | 96 | ↖ | (T) N092 Dr… | SF | -7 | 45 | Start: 2025-02-17; End: 2025-04-02
| 100 | 7 | -1 | T | N101 Drill | [5 empty] | 96 | ↖ | (T) N092 Dr… | FS | 7 | 45 | Start: 2025-06-01; End: 2025-07-15
| 101 | 7 | -1 | T | N101 Complete | [5 empty] | 100 | ↖ | (T) N101 Dr… | FS | 10 | 30 | Start: 2025-07-26; End: 2025-08-24
| 102 | 7 | -1 | T | N101 Equip | [5 empty] | 101 | ↖ | (T) N101 Co… | FS |  | 30 | Start: 2025-08-25; End: 2025-09-23
| 103 | 7 | -1 | T | P111 Drill | [5 empty] | 100 | ↖ | (T) N101 Dr… | FS | 7 | 45 | Start: 2025-07-23; End: 2025-09-05
| 104 | 7 | -1 | T | P111 Complete | [5 empty] | 103 | ↖ | (T) P111 Dr… | FS | 10 | 30 | Start: 2025-09-16; End: 2025-10-15
| 105 | 7 | -1 | T | P111 Equip | [5 empty] | 104 | ↖ | (T) P111 Co… | FS |  | 30 | Start: 2025-10-16; End: 2025-11-14
| 106 | 7 | -1 | T | N121 Drill | [5 empty] | 103 | ↖ | (T) P111 Dr… | FS | 7 | 45 | Start: 2025-09-13; End: 2025-10-27
| 107 | 7 | -1 | T | N121 Complete | [5 empty] | 106 | ↖ | (T) N121 Dr… | FS | 10 | 30 | Start: 2025-11-07; End: 2025-12-06
| 108 | 7 | -1 | T | N121 Equip | [5 empty] | 107 | ↖ | (T) N121 Co… | FS |  | 30 | Start: 2025-12-07; End: 2026-01-05
| 109 | 8 | -1 | S | MIDSTREAM CONSTRUCTION |  |  |  | 2023-10-15 |  |  |  |  | FS |  | 474 | Start: 2023-10-15; End: 2025-01-30; 2023-01-02 %: 0%
| 110 | 8 | -1 | T | W&G Trunk Lines (3) | [5 empty] | 72 | ↖ | (T) Well Pl… | SS |  | 475 | Start: 2023-10-15; End: 2025-01-31
| 111 | 9 | -1 | S | WATER OAK PLANT 1 (20MW) |  |  |  | 2022-10-15 |  |  |  |  | FS |  | 84 | Start: 2022-10-15; End: 2023-01-06; 2023-01-02 %: 20%
| 112 | 9 | -1 | T | RFP |  |  |  | 2022-10-15 |  |  |  |  | FS |  | 85 | Start: 2022-10-15; End: 2023-01-07; 2023-01-02 %: 20%
| 113 | 9 | -1 | T | Permitting | [8 empty] | FS
| 114 | 9 | -1 | T | Preliminary Design | [8 empty] | FS
| 115 | 9 | -1 | T | FEED | [8 empty] | FS
| 116 | 9 | -1 | T | Fabrication | [8 empty] | FS
| 117 | 9 | -1 | T | Mobilization | [8 empty] | FS
| 118 | 9 | -1 | T | Construction | [8 empty] | FS
| 119 | 9 | -1 | T | Installation | [8 empty] | FS
| 120 | 9 | -1 | T | Commisioning | [8 empty] | FS
| 121 | 9 | -1 | T | Transmission Design & Integration Plan | [8 empty] | FS
| 122 | 9 | -1 | T | Transmission Line Construction | [8 empty] | FS
| 123 | 9 | -1 | T | Connection/Integration | [8 empty] | FS
| 124 | 9 | -1 | T | Power Delivery & Sales | [8 empty] | FS
| 125 | FALSE | -1 | [10 empty] | FS

## Setting
Settings
Gantt
| Project Details |  |  | Project Role Types |  |  |  | Project Team
|  | Project Title: |  |  | Role | Code | # |  | Name | Role | Code
[5 empty] | Manager | MGR | 2 |  | D. Rehg | Manager | MGR
|  | Project Manager: |  |  | Project Leader | PL | 0 |  | S. Marshall | Manager | MGR
[5 empty] | Engineering | ENG | 4 |  | J. Toedter | Engineering | ENG
|  | Project Priority: | Low |  | G&G | G&G | 2 |  | B. Silva | Business Dev. | BD
[5 empty] | Petrophysics | PP | 0 |  | D. Knight | G&G | G&G
[5 empty] | Business Dev. | BD | 2 |  | J.D. Caron | Engineering | ENG
[5 empty] | Land | LAN | 0 |  | N. Cestari | Business Dev. | BD
[5 empty] | Finance | FIN | 2 |  | W. Garrett | Finance | FIN
[7 empty] | 12 |  | A. Bradley | Engineering | ENG
[9 empty] | M. Xing | Finance | FIN
[9 empty] | C. Villa | Engineering | ENG
[9 empty] | A. Pedersen | G&G | G&G