## Gantt
Engineering Project Management Dashboard
[22 empty] | Project Timespan: | [7 empty] | 2022-11-01 |  |  |  | - | 2025-03-07 |  |  |  | (614) | [22 empty] | Settings
|  | Input Column | [6 empty] | Auto Stage ind.start |  | =MIN(ITEMS_START) | [10 empty] | Color By | [9 empty] | Display | [8 empty] | Show Progress | [20 empty] | Highlight
|  | Calculated Column | [6 empty] | Auto Stage workdays |  | =NETWORKDAYS(plan_start,MAX(ITEMS_END)) | [10 empty] | Project Structure | [9 empty] | Plan | [8 empty] | No | [20 empty] | Today
|  | Snapshot Column | [6 empty] | Auto Stage % |  | =SUM(ITEMS_PERCENT*ITEMS_WORKDAYS)/SUM(ITEMS_WORKDAYS)
[10 empty] | copy this formula into a type "S" in workdays column ONLY! | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unicode Icons | [7 empty] | Actual Plan | [9 empty] | Base Plan |  | Today | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31
| ⚠ - ◆ - ⚑ - ↖ - ↙ | [7 empty] | Updated on: | [9 empty] | Saved on: |  | 0
| ids |  |  | Item Details |  |  |  |  | 2022-12-09 | [9 empty] | x-xx-x
| id | s id | r id | Type | Description | Role | Team Member | ⚠ | ind. Start | ind. End | d. id | d. Item |  | d. conn | d. lag | Work days | Start | End | Start | End | % | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M
| 1 | 1 | -1 | S | Data Gathering |  |  |  | 2023-01-01 |  |  |  |  | FS |  | 379 | Start: 2023-01-01; End: 2024-06-12; x-xx-x %: 0%
| 2 | 1 | -1 | T | Seismic Interpretation |  |  |  | 2023-01-01 |  |  |  |  | FS |  | 50 | Start: 2023-01-01; End: 2023-03-09
| 3 | 1 | -1 | T | Geologic Model | [5 empty] | 2 | ↖ | (T) Seismic… | FS |  | 14 | Start: 2023-03-10; End: 2023-03-29
| 4 | 1 | -1 | T | Reservoir Model | [5 empty] | 3 | ↖ | (T) Geologi… | FS |  | 14 | Start: 2023-03-30; End: 2023-04-18
| 5 | 1 | -1 | T | - Well Spacing/Temp/Rate Model - 20MW | [5 empty] | 4 | ↖ | (T) Reservo… | FS |  | 30 | Start: 2023-04-19; End: 2023-05-30
| 6 | 1 | -1 | T | - 20MW Full Simulation | [5 empty] | 5 | ↖ | (T) - Well … | FS |  | 30 | Start: 2023-05-31; End: 2023-07-11
| 7 | 1 | -1 | T | - 20MW Development Plan | [5 empty] | 6 | ↖ | (T) - 20MW … | SS | 5 | 60 | Start: 2023-06-07; End: 2023-08-29
| 8 | 1 | -1 | T | Core Analysis - Water Oak #1-1PV | [5 empty] | 32 | ↙ | (T) Core, L… | SS | 5 | 60 | Start: 2023-10-04; End: 2023-12-26
| 9 | 1 | -1 | T | Reservoir Test Analysis - Water Oak #1 - 1PV | [5 empty] | 38 | ↙ | (T) Flow Te… | SS | 5 | 75 | Start: 2024-03-01; End: 2024-06-13
| 10 | 2 | -1 | S | PURE #1 ACTIVITIES |  |  |  | 2022-12-12 |  |  |  |  | FS |  | 140 | Start: 2022-12-12; End: 2023-06-23; x-xx-x %: 11.95%
| 11 | 2 | -1 | T | Acquisition |  |  |  | 2022-12-12 | 2023-01-31 |  |  |  | SS | -10 | 35 | Start: 2022-12-12; End: 2023-01-27; x-xx-x %: 70%
| 12 | 2 | -1 | T | SUA & Damages |  |  | ⚠ |  |  | 11 | ↖ | (T) Acquisi… | FS | -10 | 30 | Start: 2023-01-16; End: 2023-02-24
| 13 | 2 | -1 | T | Surface Site Prep | [5 empty] | 12 | ↖ | (T) SUA & D… | FS |  | 30 | Start: 2023-02-27; End: 2023-04-07
| 14 | 2 | -1 | T | Conversion CWOP | [5 empty] | 12 | ↖ | (T) SUA & D… | SS |  | 31 | Start: 2023-01-16; End: 2023-02-27; x-xx-x %: 10%
| 15 | 2 | -1 | T | Permitting | [5 empty] | 11 | ↖ | (T) Acquisi… | FS |  | 91 | Start: 2023-01-30; End: 2023-06-05
| 16 | 2 | -1 | T | Workover & Testing | [5 empty] | 15 | ↖ | (T) Permitt… | FS |  | 14 | Start: 2023-06-06; End: 2023-06-23
| 17 | 3 | -1 | S | PURE #1D ACTIVITIES |  |  |  | 2022-12-12 |  |  |  |  | FF |  | 585 | Start: 2022-12-12; End: 2025-03-07; x-xx-x %: 9.423%
| 18 | 3 | -1 | T | Acquisition | [5 empty] | 11 | ↖ | (T) Acquisi… | SS |  | 35 | Start: 2022-12-12; End: 2023-01-27; x-xx-x %: 70%
| 19 | 3 | -1 | T | Surface Site Prep, Facilities Repair & Inj Tests | [5 empty] | 13 | ↖ | (T) Surface… | SS |  | 30 | Start: 2023-02-27; End: 2023-04-07
| 20 | 3 | -1 | T | Workover & Remediation | [5 empty] | 16 | ↖ | (T) Workove… | FS |  | 14 | Start: 2023-06-26; End: 2023-07-13
| 21 | 3 | -1 | T | Disposal Operations | [5 empty] | 38 | ↙ | (T) Flow Te… | FS |  | 91 | Start: 2024-04-05; End: 2024-08-09
| 22 | 3 | -1 | T | Surface Equipment Removal | [5 empty] | 21 | ↖ | (T) Disposa… | FS | 60 | 90 | Start: 2024-11-04; End: 2025-03-07
| 23 | 4 | -1 | S | WATER OAK 1 P011CR |  |  |  | 2022-11-01 |  |  |  |  | FS |  | 404 | Start: 2022-11-01; End: 2024-05-17; x-xx-x %: 16.19%
| 24 | 4 | -1 | T | OCTG Order |  |  |  | 2022-12-12 | 2023-03-31 |  |  |  | FS |  | 80 | Start: 2022-12-12; End: 2023-03-31; x-xx-x %: 38%
| 25 | 4 | -1 | T | Internal coating for production casing | [5 empty] | 24 | ↖ | (T) OCTG Or… | FS | 7 | 50 | Start: 2023-04-12; End: 2023-06-20; x-xx-x %: 5%
| 26 | 4 | -1 | T | Wellhead Order |  |  | ⚠ | 2022-12-16 |  |  |  |  | SS |  | 100 | Start: 2022-12-16; End: 2023-05-04; x-xx-x %: 60%
| 27 | 4 | -1 | T | Land Work, SUA & Damages |  |  | ⚠ | 2022-11-01 |  |  |  |  | FS |  | 60 | Start: 2022-11-01; End: 2023-01-23
| 28 | 4 | -1 | T | Environmental & Permitting |  |  | ⚠ | 2022-12-19 |  |  |  |  | FS |  | 120 | Start: 2022-12-19; End: 2023-06-02; x-xx-x %: 10%
| 29 | 4 | -1 | T | Pad Construction & Conductor |  |  |  | 2023-03-01 |  |  |  |  | FS |  | 30 | Start: 2023-03-01; End: 2023-04-11
| 30 | 4 | -1 | T | Final Drill Plan and DWOP |  |  |  | 2023-05-15 |  | 29 | ↖ | (T) Pad Con… | SS |  | 60 | Start: 2023-05-15; End: 2023-08-04
| 31 | 4 | -1 | T | Drill to core point (Patterson 346) | [5 empty] | 30 | ↖ | (T) Final D… | FS | 7 | 30 | Start: 2023-08-16; End: 2023-09-26
| 32 | 4 | -1 | T | Core, Log & Run Pipe | [5 empty] | 31 | ↖ | (T) Drill t… | FS |  | 15 | Start: 2023-09-27; End: 2023-10-17
| 33 | 4 | -1 | T | Wait on data processing for log & core | [8 empty] | FS
| 34 | 4 | -1 | T | Completion Planning & CWOP | [5 empty] | 8 | ↖ | (T) Core An… | FS |  | 14 | Start: 2023-12-27; End: 2024-01-15
| 35 | 4 | -1 | T | Completion Operations | [5 empty] | 34 | ↖ | (T) Complet… | FS |  | 14 | Start: 2024-01-16; End: 2024-02-02
| 36 | 4 | -1 | T | Perforate and DFIT's (5 intervals) | [5 empty] | 35 | ↖ | (T) Complet… | FS |  | 10 | Start: 2024-02-05; End: 2024-02-16
| 37 | 4 | -1 | T | Set Packer & Tube Up | [5 empty] | 36 | ↖ | (T) Perfora… | FS |  | 4 | Start: 2024-02-19; End: 2024-02-22
| 38 | 4 | -1 | T | Flow Test | [5 empty] | 37 | ↖ | (T) Set Pac… | FS |  | 30 | Start: 2024-02-23; End: 2024-04-04
| 39 | 4 | -1 | T | PDD & PBU | [5 empty] | 38 | ↖ | (T) Flow Te… | FS |  | 21 | Start: 2024-04-05; End: 2024-05-03
| 40 | 4 | -1 | T | Turn in Line | [5 empty] | 39 | ↖ | (T) PDD & P… | FS |  | 10 | Start: 2024-05-06; End: 2024-05-17
| 41 | 5 | -1 | S | WATER OAK 1 D021 |  |  |  | 2022-11-01 |  |  |  |  | FS |  | 338 | Start: 2022-11-01; End: 2024-02-15; x-xx-x %: 11.89%
| 42 | 5 | -1 | T | OCTG Order |  |  | ⚠ |  |  | 24 | ↖ | (T) OCTG Or… | SS |  | 80 | Start: 2022-12-12; End: 2023-03-31; x-xx-x %: 70%
| 43 | 5 | -1 | T | Wellhead Order |  |  | ⚠ |  |  | 26 | ↖ | (T) Wellhea… | SS |  | 3 | Start: 2022-12-16; End: 2022-12-20
| 44 | 5 | -1 | T | Land Work, SUA & Damages |  |  | ⚠ |  |  | 27 | ↖ | (T) Land Wo… | SS |  | 60 | Start: 2022-11-01; End: 2023-01-23
| 45 | 5 | -1 | T | Permitting & Follow-up notifications |  |  | ⚠ |  |  | 28 | ↖ | (T) Environ… | SS | 7 | 180 | Start: 2022-12-28; End: 2023-09-05
| 46 | 5 | -1 | T | Pad Construction & Conductor | [5 empty] | 29 | ↖ | (T) Pad Con… | FS |  | 30 | Start: 2023-04-12; End: 2023-05-23
| 47 | 5 | -1 | T | Final Drill Plan and DWOP | [5 empty] | 30 | ↖ | (T) Final D… | FS |  | 45 | Start: 2023-08-07; End: 2023-10-06
| 48 | 5 | -1 | T | Drill to TD | [5 empty] | 32 | ↖ | (T) Core, L… | FS | 7 | 20 | Start: 2023-10-27; End: 2023-11-23
| 49 | 5 | -1 | T | Log & Run pipe | [5 empty] | 48 | ↖ | (T) Drill t… | FS |  | 5 | Start: 2023-11-24; End: 2023-11-30
| 50 | 5 | -1 | T | Completion Planning & CWOP | [5 empty] | 49 | ↖ | (T) Log & R… | FS | 7 | 14 | Start: 2023-12-12; End: 2023-12-29
| 51 | 5 | -1 | T | Completion Operations | [5 empty] | 50 | ↖ | (T) Complet… | FS |  | 7 | Start: 2024-01-01; End: 2024-01-09
| 52 | 5 | -1 | T | Perforate (3 intervals) | [5 empty] | 51 | ↖ | (T) Complet… | FS |  | 10 | Start: 2024-01-10; End: 2024-01-23
| 53 | 5 | -1 | T | Set Packer & Tube Up | [5 empty] | 52 | ↖ | (T) Perfora… | FS |  | 10 | Start: 2024-01-24; End: 2024-02-06
| 54 | 5 | -1 | T | Put well in service | [5 empty] | 53 | ↖ | (T) Set Pac… | FS |  | 7 | Start: 2024-02-07; End: 2024-02-15
| 55 | 6 | -1 | S | FACILITIES CONSTRUCTION |  |  |  | 2023-01-05 |  |  |  |  | FS |  | 274 | Start: 2023-01-05; End: 2024-01-23; x-xx-x %: 0%
| 56 | 6 | -1 | T | Design Facilities |  |  | ⚠ | 2023-01-05 |  |  |  |  | FS |  | 14 | Start: 2023-01-05; End: 2023-01-24
| 57 | 6 | -1 | T | Gas Marketing Agreements |  |  | ⚠ |  |  | 56 | ↖ | (T) Design … | SS |  | 30 | Start: 2023-01-05; End: 2023-02-15
| 58 | 6 | -1 | T | Order Equipment |  |  | ⚠ |  |  | 56 | ↖ | (T) Design … | FS |  | 120 | Start: 2023-01-25; End: 2023-07-11
| 59 | 6 | -1 | T | Equip new wells | [5 empty] | 32 | ↖ | (T) Core, L… | FS | 10 | 60 | Start: 2023-11-01; End: 2024-01-23
| 60 | 6 | -1 | T | W/G Production and Injection Line Installation | [5 empty] | 59 | ↖ | (T) Equip n… | SS |  | 60 | Start: 2023-11-01; End: 2024-01-23
| 61 | 7 | -1 | S | CYMRIC 1MW ORC |  |  |  | 2022-12-01 |  |  |  |  | FS |  | 372 | Start: 2022-12-01; End: 2024-05-03; x-xx-x %: 3.415%
| 62 | 7 | -1 | T | Acquisition |  |  |  | 2022-12-01 |  |  |  |  | FS |  | 30 | Start: 2022-12-01; End: 2023-01-11; x-xx-x %: 70%
| 63 | 7 | -1 | T | Site Selection/Survey/Permitting | [5 empty] | 62 | ↖ | (T) Acquisi… | FS |  | 45 | Start: 2023-01-12; End: 2023-03-15
| 64 | 7 | -1 | T | SUA & Damages | [5 empty] | 63 | ↖ | (T) Site Se… | SS |  | 60 | Start: 2023-01-12; End: 2023-04-05
| 65 | 7 | -1 | T | Transmission Design & Integration Plan | [5 empty] | 63 | ↖ | (T) Site Se… | SS |  | 90 | Start: 2023-01-12; End: 2023-05-17
| 66 | 7 | -1 | T | Construct Pad and Civil Works | [5 empty] | 64 | ↖ | (T) SUA & D… | FS |  | 30 | Start: 2023-04-06; End: 2023-05-17
| 67 | 7 | -1 | T | Installation, Repairs & Refurbishment | [5 empty] | 66 | ↖ | (T) Constru… | SF | 60 | 90 | Start: 2023-02-23; End: 2023-06-28
| 68 | 7 | -1 | T | Transmission Line Construction | [5 empty] | 66 | ↖ | (T) Constru… | SS | 20 | 60 | Start: 2023-05-04; End: 2023-07-26
| 69 | 7 | -1 | T | Testing & Commissioning | [5 empty] | 71 | ↙ | (T) Power D… | SF |  | 90 | Start: 2023-10-09; End: 2024-02-09
| 70 | 7 | -1 | T | Connection/Integration | [5 empty] | 71 | ↙ | (T) Power D… | SF |  | 60 | Start: 2023-11-20; End: 2024-02-09
| 71 | 7 | -1 | T | Power Delivery & Sales | [5 empty] | 40 | ↖ | (T) Turn in… | SF |  | 60 | Start: 2024-02-12; End: 2024-05-03
| 72 | 8 | -1 | S | PHASE II DEVELOPMENT |  |  |  | 2023-06-07 |  |  |  |  | FS |  | 823 | Start: 2023-06-07; End: 2026-07-31; x-xx-x %: 0%
| 73 | 8 | -1 | T | Land/Lease | [5 empty] | 7 | ↖ | (T) - 20MW … | SS |  | 60 | Start: 2023-06-07; End: 2023-08-29
| 74 | 8 | -1 | T | SUA & Damages | [5 empty] | 73 | ↖ | (T) Land/Le… | FS | -30 | 60 | Start: 2023-07-19; End: 2023-10-10
| 75 | 8 | -1 | T | Permitting | [5 empty] | 73 | ↖ | (T) Land/Le… | FS | -30 | 180 | Start: 2023-07-19; End: 2024-03-26
| 76 | 8 | -1 | T | Order Tubulars & Wellheads | [5 empty] | 7 | ↖ | (T) - 20MW … | FS |  | 270 | Start: 2023-08-30; End: 2024-09-10
| 77 | 8 | -1 | T | Order Surface Facilities for 22 thru 92 | [5 empty] | 7 | ↖ | (T) - 20MW … | FS |  | 270 | Start: 2023-08-30; End: 2024-09-10
| 78 | 8 | -1 | T | Well Plans & DWOP | [5 empty] | 75 | ↖ | (T) Permitt… | FS | -45 | 120 | Start: 2024-01-24; End: 2024-07-09
| 79 | 8 | -1 | T | Pad & Cond - WO1 P022, P032, N042, N052 | [5 empty] | 75 | ↖ | (T) Permitt… | FS | -10 | 60 | Start: 2024-03-13; End: 2024-06-04
| 80 | 8 | -1 | T | P022 Drill WO1 | [5 empty] | 76 | ↖ | (T) Order T… | FS | 14 | 45 | Start: 2024-10-01; End: 2024-12-02
| 81 | 8 | -1 | T | P022 Complete WO1 | [5 empty] | 80 | ↖ | (T) P022 Dr… | FS | 10 | 30 | Start: 2024-12-17; End: 2025-01-27
| 82 | 8 | -1 | T | P022 Equip WO1 | [5 empty] | 81 | ↖ | (T) P022 Co… | SS |  | 30 | Start: 2024-12-17; End: 2025-01-27
| 83 | 8 | -1 | T | P032 Drill WO1 | [5 empty] | 80 | ↖ | (T) P022 Dr… | FS | 7 | 45 | Start: 2024-12-12; End: 2025-02-12
| 84 | 8 | -1 | T | P032 Complete WO1 | [5 empty] | 83 | ↖ | (T) P032 Dr… | FS | 10 | 30 | Start: 2025-02-27; End: 2025-04-09
| 85 | 8 | -1 | T | P032 Equip WO1 | [5 empty] | 84 | ↖ | (T) P032 Co… | SS |  | 30 | Start: 2025-02-27; End: 2025-04-09
| 86 | 8 | -1 | T | N042 Drill WO1 | [5 empty] | 83 | ↖ | (T) P032 Dr… | FS | 7 | 45 | Start: 2025-02-24; End: 2025-04-25
| 87 | 8 | -1 | T | N042 Complete WO1 | [5 empty] | 86 | ↖ | (T) N042 Dr… | FS | 10 | 30 | Start: 2025-05-12; End: 2025-06-20
| 88 | 8 | -1 | T | N042 Equip WO1 | [5 empty] | 87 | ↖ | (T) N042 Co… | SS |  | 30 | Start: 2025-05-12; End: 2025-06-20
| 89 | 8 | -1 | T | NO52 Drill WO1 | [5 empty] | 86 | ↖ | (T) N042 Dr… | FS | 7 | 45 | Start: 2025-05-07; End: 2025-07-08
| 90 | 8 | -1 | T | NO52 Complete WO1 | [5 empty] | 89 | ↖ | (T) NO52 Dr… | FS | 10 | 30 | Start: 2025-07-23; End: 2025-09-02
| 91 | 8 | -1 | T | NO52 Equip WO1 | [5 empty] | 90 | ↖ | (T) NO52 Co… | SS |  | 30 | Start: 2025-07-23; End: 2025-09-02
| 92 | 8 | -1 | T | Pad & Cond - WO1 P062, P072, N082, N092 | [5 empty] | 89 | ↖ | (T) NO52 Dr… | SF | -14 | 60 | Start: 2025-01-23; End: 2025-04-16
| 93 | 8 | -1 | T | P062 Drill | [5 empty] | 89 | ↖ | (T) NO52 Dr… | FS | 7 | 45 | Start: 2025-07-18; End: 2025-09-18
| 94 | 8 | -1 | T | P062 Complete | [5 empty] | 93 | ↖ | (T) P062 Dr… | FS | 10 | 30 | Start: 2025-10-03; End: 2025-11-13
| 95 | 8 | -1 | T | P062 Equip | [5 empty] | 94 | ↖ | (T) P062 Co… | FS |  | 30 | Start: 2025-11-14; End: 2025-12-25
| 96 | 8 | -1 | T | P072 Drill | [5 empty] | 93 | ↖ | (T) P062 Dr… | FS | 7 | 45 | Start: 2025-09-30; End: 2025-12-01
| 97 | 8 | -1 | T | P072 Complete | [5 empty] | 96 | ↖ | (T) P072 Dr… | FS | 10 | 30 | Start: 2025-12-16; End: 2026-01-26
| 98 | 8 | -1 | T | P072 Equip | [5 empty] | 97 | ↖ | (T) P072 Co… | FS |  | 30 | Start: 2026-01-27; End: 2026-03-09
| 99 | 8 | -1 | T | N082 Drill | [5 empty] | 96 | ↖ | (T) P072 Dr… | FS | 7 | 45 | Start: 2025-12-11; End: 2026-02-11
| 100 | 8 | -1 | T | N082 Complete | [5 empty] | 99 | ↖ | (T) N082 Dr… | FS | 10 | 30 | Start: 2026-02-26; End: 2026-04-08
| 101 | 8 | -1 | T | N082 Equip | [5 empty] | 100 | ↖ | (T) N082 Co… | FS |  | 30 | Start: 2026-04-09; End: 2026-05-20
| 102 | 8 | -1 | T | N092 Drill | [5 empty] | 99 | ↖ | (T) N082 Dr… | FS | 7 | 45 | Start: 2026-02-23; End: 2026-04-24
| 103 | 8 | -1 | T | N092 Complete | [5 empty] | 102 | ↖ | (T) N092 Dr… | FS | 10 | 30 | Start: 2026-05-11; End: 2026-06-19
| 104 | 8 | -1 | T | N092 Equip | [5 empty] | 103 | ↖ | (T) N092 Co… | FS |  | 30 | Start: 2026-06-22; End: 2026-07-31
| 105 | 8 | -1 | T | Conductor - WO1 N101, P111, N121 | [5 empty] | 102 | ↖ | (T) N092 Dr… | SF | -7 | 45 | Start: 2025-12-11; End: 2026-02-11
| 106 | 8 | -1 | T | N101 Drill | [5 empty] | 102 | ↖ | (T) N092 Dr… | FS | 7 | 45 | Start: 2026-05-06; End: 2026-07-07
| 107 | 8 | -1 | T | N101 Complete | [5 empty] | 106 | ↖ | (T) N101 Dr… | FS | 10 | 30 | Start: 2026-07-22; End: 2026-09-01
| 108 | 8 | -1 | T | N101 Equip | [5 empty] | 107 | ↖ | (T) N101 Co… | FS |  | 30 | Start: 2026-09-02; End: 2026-10-13
| 109 | 8 | -1 | T | P111 Drill | [5 empty] | 106 | ↖ | (T) N101 Dr… | FS | 7 | 45 | Start: 2026-07-17; End: 2026-09-17
| 110 | 8 | -1 | T | P111 Complete | [5 empty] | 109 | ↖ | (T) P111 Dr… | FS | 10 | 30 | Start: 2026-10-02; End: 2026-11-12
| 111 | 8 | -1 | T | P111 Equip | [5 empty] | 110 | ↖ | (T) P111 Co… | FS |  | 30 | Start: 2026-11-13; End: 2026-12-24
| 112 | 8 | -1 | T | N121 Drill | [5 empty] | 109 | ↖ | (T) P111 Dr… | FS | 7 | 45 | Start: 2026-09-29; End: 2026-11-30
| 113 | 8 | -1 | T | N121 Complete | [5 empty] | 112 | ↖ | (T) N121 Dr… | FS | 10 | 30 | Start: 2026-12-15; End: 2027-01-25
| 114 | 8 | -1 | T | N121 Equip | [5 empty] | 113 | ↖ | (T) N121 Co… | FS |  | 30 | Start: 2027-01-26; End: 2027-03-08
| 115 | 9 | -1 | S | MIDSTREAM CONSTRUCTION |  |  |  | 2024-01-24 |  |  |  |  | FS |  | 475 | Start: 2024-01-24; End: 2025-11-18; x-xx-x %: 0%
| 116 | 9 | -1 | T | W&G Trunk Lines (3) | [5 empty] | 78 | ↖ | (T) Well Pl… | SS |  | 475 | Start: 2024-01-24; End: 2025-11-18
| 117 | 10 | -1 | S | WATER OAK PLANT 1 (20MW) |  |  |  | 2022-10-15 |  |  |  |  | FS |  | 84 | Start: 2022-10-15; End: 2023-02-08; x-xx-x %: 20%
| 118 | 10 | -1 | T | RFP |  |  |  | 2022-10-15 |  |  |  |  | FS |  | 85 | Start: 2022-10-15; End: 2023-02-09; x-xx-x %: 20%
| 119 | 10 | -1 | T | Permitting | [8 empty] | FS
| 120 | 10 | -1 | T | Preliminary Design | [8 empty] | FS
| 121 | 10 | -1 | T | FEED | [8 empty] | FS
| 122 | 10 | -1 | T | Fabrication | [8 empty] | FS
| 123 | 10 | -1 | T | Mobilization | [8 empty] | FS
| 124 | 10 | -1 | T | Construction | [8 empty] | FS
| 125 | 10 | -1 | T | Installation | [8 empty] | FS
| 126 | 10 | -1 | T | Commisioning | [8 empty] | FS
| 127 | 10 | -1 | T | Transmission Design & Integration Plan | [8 empty] | FS
| 128 | 10 | -1 | T | Transmission Line Construction | [8 empty] | FS
| 129 | 10 | -1 | T | Connection/Integration | [8 empty] | FS
| 130 | 10 | -1 | T | Power Delivery & Sales | [8 empty] | FS
| 131 | FALSE | -1 | [10 empty] | FS

## Setting
Settings
Gantt
| Project Details |  |  | Project Role Types |  |  |  | Project Team
|  | Project Title: |  |  | Role | Code | # |  | Name | Role | Code
[5 empty] | Manager | MGR | 2 |  | D. Rehg | Manager | MGR
|  | Project Manager: |  |  | Project Leader | PL | 0 |  | S. Marshall | Manager | MGR
[5 empty] | Engineering | ENG | 4 |  | J. Toedter | Engineering | ENG
|  | Project Priority: | Low |  | G&G | G&G | 2 |  | B. Silva | Business Dev. | BD
[5 empty] | Petrophysics | PP | 0 |  | D. Knight | G&G | G&G
[5 empty] | Business Dev. | BD | 2 |  | J.D. Caron | Engineering | ENG
[5 empty] | Land | LAN | 0 |  | N. Cestari | Business Dev. | BD
[5 empty] | Finance | FIN | 2 |  | W. Garrett | Finance | FIN
[7 empty] | 12 |  | A. Bradley | Engineering | ENG
[9 empty] | M. Xing | Finance | FIN
[9 empty] | C. Villa | Engineering | ENG
[9 empty] | A. Pedersen | G&G | G&G